| ENGINEERING TIMESHEET Project #5: North Dakota Pipeline Water Quality Analysis | Team Members Ayub Abdi Eli Speth |
| --- | --- |

| PROJECT WINDOW April 6 – May 7, 2026 |  | TOTAL PROJECT HOURS 42 hours |  | TOTAL COMPENSATION $924 |
| --- | --- | --- | --- | --- |
| Course | CIVE 202 – Civil Engineering Analysis II |  | Client / Project | Garrison Diversion Project / RRVWSP |
| Rate Used | $22 per hour |  | Purpose | Track engineering labor, tasks, and compensation |

Detailed Time Log

| Day | Date | Engineer | Hours | Task Completed | Rate | Comp. |
| --- | --- | --- | --- | --- | --- | --- |
| Monday | 4/6/26 | Ayub Abdi | 1.5 | Draft Scope of Work and define project goals | $22 | $33 |
| Monday | 4/6/26 | Eli Speth | 1.5 | Review client prompt and water quality requirements | $22 | $33 |
| Tuesday | 4/7/26 | Ayub Abdi | 2 | Environment setup: install and implement Python packages | $22 | $44 |
| Tuesday | 4/7/26 | Eli Speth | 2 | Import USGS North Dakota water quality CSV and canal location file | $22 | $44 |
| Wednesday | 4/8/26 | Ayub Abdi | 2 | Clean dataset and standardize column names | $22 | $44 |
| Wednesday | 4/8/26 | Eli Speth | 2 | Check units, dates, and numeric result values | $22 | $44 |
| Thursday | 4/9/26 | Ayub Abdi | 2 | Filter major cations, major anions, TDS, pH, temperature, and hardness | $22 | $44 |
| Friday | 4/10/26 | Eli Speth | 2 | Organize records by McClusky Canal monitoring locations | $22 | $44 |
| Monday | 4/13/26 | Ayub Abdi | 2 | Compute mean, median, minimum, and maximum summary statistics | $22 | $44 |
| Tuesday | 4/14/26 | Eli Speth | 3 | Generate four boxplots and spatial trend plots | $22 | $66 |
| Wednesday | 4/15/26 | Ayub Abdi | 2 | Create reusable functions for parameter grouping and statistics | $22 | $44 |
| Thursday | 4/16/26 | Eli Speth | 2 | Create comparison tables and review downstream trends | $22 | $44 |
| Monday | 4/20/26 | Ayub Abdi | 3 | Complete mass loading calculations using Q x C | $22 | $66 |
| Tuesday | 4/21/26 | Eli Speth | 2 | Account for canal water entering the Sheyenne River | $22 | $44 |
| Wednesday | 4/22/26 | Ayub Abdi | 3 | Develop dynamic TDS mixing model for Lake Ashtabula | $22 | $66 |
| Wednesday | 4/22/26 | Eli Speth | 2 | Run scenario testing for flow and concentration cases | $22 | $44 |
| Thursday | 4/23/26 | Ayub Abdi | 2 | Validate results and compare observed trends | $22 | $44 |
| Friday | 4/24/26 | Eli Speth | 2 | Conduct bias and ethics review of coding decisions | $22 | $44 |
| Monday | 4/27/26 | Ayub Abdi | 2 | Prepare Annotated Code Document and project summaries | $22 | $44 |
| Thursday | 5/7/26 | Eli Speth | 2 | Compile final report figures, GitHub files, timesheet, and submission review | $22 | $44 |
| TOTAL PROJECT BILLING |  |  | 42 | Total hours and compensation |  | $924 |

Labor Distribution Summary

| Engineer | Total Hours | Hourly Rate | Total Compensation |
| --- | --- | --- | --- |
| Ayub Abdi | 21.5 | $22 | $473 |
| Eli Speth | 20.5 | $22 | $451 |

Phase Breakdown

| Project Phase | Hours | Main Work Included |
| --- | --- | --- |
| Planning | 3 | Scope of work and client prompt review |
| Setup | 4 | Python environment and input datasets |
| Processing | 8 | Cleaning, unit checks, parameters, and locations |
| Analysis | 9 | Statistics, boxplots, spatial trends, comparison tables |
| Modeling | 10 | Mass loading, river integration, TDS model, simulations |
| QA / Review | 4 | Validation, trend checking, ethics review |
| Documentation | 4 | ACD, summaries, GitHub files, final submission review |